## Sheet1
Group #3 Project Plan
Project | A
Captain | Tyler Roussos
Group Members | Giuseppe Dibella | Louis Reynolds
Date | Group | Giuseppe Dibella | Louis Reynolds | Tyler Roussos
2014-09-17 | 1) Research PHP Frameworks and Drupal's Viability 2) Investigate different frontend CSS Frameworks 3) Decide on Javascript framework, or whether to do it all in PHP 4) Determine Roles of users 5) Wrap up the ERR basis | 1) Decide on Javascript Framework 2) Determine Role of users | 1) Wrap up ERR basis | 1) Research PHP Frameworks and Drupal's Viability 2) Investigate CSS Frameworks
2014-09-24 | 1) Create Base Entities in PHP Framework 2) Setup CRUD parent template 3) Research security in the PHP Framework 4) Wrap up any outstanding paperwork 5) Setup base site styling | 1) Research Security in the PHP Framework 2) Setup secured area and login | 1) Wrap up any outstanding paperwork 2) Create Base Entities | 1) Setup CRUD parent tempalte 2) Setup base site template
2014-10-01 | 1) Fully devlop crud for each entity 2) Scaffold all of the needed CRUD forms 3) Layout the UI | 1) Create the CRUD backend support | 1) Create the CRUD forms 2) Setup Search and daterange filtering | 1) Layout the UI and overall flow
2014-10-08 | 1) Final UAT Testing 2) Production Deployment onto development server | 1) Backend and database bug fixes | 1) Perform UAT Testing and file any bugs found | 1) UI and Interaction Bug Fixes 2) Deploy final app
2014-10-15 | 1) Project complete 2) Prepare for presentation